## FF&E schedule
FF&E schedule
One row per specified item. Net unit and line total calculate themselves. Free template from vade.design/tools/ffe-schedule-template
Ref | Room | Zone | Item | Description / specification | Supplier | Product code | Finish / colourway | Dimensions (mm) | Qty | Unit cost ex VAT | Trade disc % | Net unit | Line total | Lead time (weeks) | Order by | Status | Product URL | Notes
01 | Drawing room | Seating | Three-seat sofa | Bench-seat sofa, feather and down wrap, castors front | Example supplier | EX-3200 | Bouclé, oat | 2200 x 950 x 780 | 1 | 2450 | 25 |  |  | 10-12 | 2026-08-15 | Specified | https://example.co.uk/product | Confirm castor finish before ordering
Schedule total ex VAT

## How to use
FF&E schedule
One row per specified item. Net unit and line total are formulas, leave them alone.
Enter the list price ex VAT in Unit cost and your discount in Trade disc, and the
rest calculates. The total at the foot of the sheet sums the line totals.
Ref
Keep it stable. It is what appears on drawings, on the board, and in the
conversation six months from now when something needs replacing.
Product URL
The single most valuable column and the one most schedules omit. A row without a
working link is a memory. A row with one is an order waiting to happen.
Order by
Work backwards from the install date using the lead time you have actually
experienced from that supplier, not the one on their website.
Status
Proposed, Specified, Approved, Ordered, Delivered, Discontinued, Rejected.
Filter on Discontinued once a quarter and clear those rows out, or you will
re-specify something that no longer exists.
This is a schedule, not a procurement system. It will not raise purchase orders,
chase deliveries or reconcile invoices. If you need that, you need a procurement
platform, and it will cost considerably more than a spreadsheet.
Free template from VADE (vade.design), the sourcing library for interior designers.
vade.design/tools/ffe-schedule-template